## IssueLog
SDMX SWG Action Log |  |  | Available here: | https://community.oecd.org/docs/DOC-96178
Update the SDMX workplan
Description | Status | Resp | References | Comments
Creation of a page for the Global Registry | Implemented | Danny Delcambre, David | https://community.oecd.org/thread/21458 | Redesign of the current landing page, making it more useful. Creation of a page for the Global Registry (reusing info from former page https://registry.sdmx.org/). This page could be a simple introductory page, providing general info on the GR and referring to the actual place where the Registry is held. Other questions are e.g.: What do we do with the existing documentation ? It can partially prove useful but looks a bit outdated (especially for screenshots) and would therefore need to be updated. The new GR page should have the same feel and look of the sdmx.org. David to follow-up ECB and Secretariat. . This is on the test instance of the GR.
Create implementation checklist for data providers. | Implemented | David | https://community.oecd.org/thread/19881 | Accepted
Extension of CL_OBS_STATUS with two new codes for Education DSD purposes | Implemented | Javier | https://community.oecd.org/thread/14150?start=150&tstart=0 | Accepted
Clean up the ClearSpace page | Closed | David |  | Many discussions could be archived (an "Archives" sub-section already exists). Asked Clearspace team but no quick bulk archiving solution
Checklist for SDMX Design Projects | Implemented |  | http://www1.unece.org/stat/platform/display/SDMXPM/Checklist+for+SDMX+Design+Projects+Home | Published. David to present it at the end of the year to standards team as an example of usng GDBPM logic for better readability
Guidelines for SDMX Concept Roles. | Implemented | Laura, David | https://community.oecd.org/thread/18002 | Published
CDCL for "Time Transformation' | Implemented |  |  | Accepted
SDMX Message Header Guidelines | Implemented | Zlatina | https://community.oecd.org/thread/19404 | To consolidate the document we have now in order to discuss the proposal
CL_AREA | Implemented | Ian | https://community.oecd.org/thread/13975 | Incorporate M49 and ISO hierarchy in separate branches. Top level nodes: M49, ISO3166_2. Add sentence to guideline about the StructureSet.
CL_ORGANISATION. Start with a flat list. Consider using HCLS later. | Implemented | Christine, Zlatina, David | https://community.oecd.org/thread/15072 | Approved 15/4/2021
Terms of Reference for the SWG | Implemented | David | https://community.oecd.org/thread/14273 | To review by SWG
Issue note on SDMX Registries | Closed | David | https://community.oecd.org/thread/19882 | See latest comments in thread. Need to update the proposal along those lines
Modelling Statistical Domains in SDMX | Implemented | David, Daniel, Ian, Laura, Zlatina | https://community.oecd.org/docs/DOC-115616 | In public review, need to address the feedback, refresh the document
Revision process for the SDMX Glossary | Closed |  | https://community.oecd.org/thread/20786 | Add a paragraph to the glossary on a revision process. Postpone until after current revision
Clickable SDMX. Follow-up on the feedback from IMF and OECD, see what is needed to publish | Implemented | Laura, David | http://www1.unece.org/stat/platform/display/ClickSDMX/Clickable+SDMX+Home | Released
Revise the "Governance of Commonly Used SDMX Metadata Artefacts" document | Closed | Danny | https://community.oecd.org/thread/15087 | Published
Global Metadata Concept Scheme proposal | Implemented | Danny, David | https://community.oecd.org/thread/20573 | Done, published. Feedback from SDGs
Populating the FAQ section on sdmx.org | Cancelled | Danny |  | In principle, this task is for the sdmx.org content manager but SWG/TWG could provide useful input for that section of the site
Guidelines for handling non-calendar years in SDMX | Implemented |  | https://community.oecd.org/thread/19921
CL_REF_PERIOD_DTL | Cancelled |  |  | Should we reactivate the discussion on this CDCL ? Was any need expressed ?
Add Information model to clickable SDMX on one page | Cancelled | Laura | http://www1.unece.org/stat/platform/display/ClickSDMX/SDMX+on+one+page
Share work on SDMX-on-one-page with secretariat | Cancelled | David
Send list of SWG members to UNECE for access to clickable SDMX | Closed | David
ask IMF/AFDB colleagues for participating in subgroup multidomain/dissemination DSDS; circulate first draft | Implemented | David | https://community.oecd.org/message/33009#33009 | Rafik confirms participation, Paul asks to join subgroup.
implementation checklist for data providers, turn more into checklist, consider Gliphi | Cancelled | Laura | https://community.oecd.org/message/33176#33176
Checklist for implementing SDMX in statistical domain to Secretariat after deadline for comments. Jin to put Secrtariat comments on Clearspace. Daniel to check which comments can be accepted and which not. | Cancelled | David, Daniel, Jin | Checklist for the implementation of SDMX in a statistical domain http://www1.unece.org/stat/platform/display/SDMXPM/Checklist+for+SDMX+Design+Projects+Home
for 029: send mock-up page and make star diagram bigger and clickable. Indicate by putting transparent text over clickable area. Page in grey. After dealine for comments. | Cancelled | Daniel
for 029: David to inform Secretariat about new page | Cancelled | David
Education DSD. Create new thread in Clearspace and post the OBS_STATUS document draft. Set deadline for comments. David and Paul to check internally by 21/04 | Cancelled | Javier, David, Paul
guidelines on non-calendar years, update and send to Secretariat | Cancelled | Daniel
registry issues document, contact TWG chairs proposing task force for registry issues | Cancelled | David |  | Marco and Chris were involved
SDMX Header guidelines, comments welcome. Add examples (from Sami's document). Paul to check content. | Cancelled | Paul
make SDMX Workplan visible in Clearspace | Implemented | David
create SDMX SWG action log | Implemented | Daniel
CL_ORGANISATION, formulate questions and ALL to provide answers | Cancelled | Danny, ALL | CL_ORGANISATION (previously referred to as CL_AGENCY
CL_TRANSFORMATION proposal on two dimensions and legacy codes treatment, comments invited. Paul to integrate two solutions. | Implemented | Paul | CL_TRANSFORMATION (Code list for time transformation)
Candidate codelist: CL_LANGUAGE, provide info on ISO-639-1 | Cancelled | Danny | https://community.oecd.org/thread/20610 | On hold until we have a use case
Addition of generic codes to codelists, start Clearspace thread | Cancelled | Danny, ALL
Clearspace site improvements: show outstanding actions. See item 014. | Implemented | David
Statistical Domains: Create a CDCL and Category Scheme | Implemented | Danny | https://community.oecd.org/thread/20430 | Sent to secretariat.
SDMX Experts meeting: Discuss capacity building & content | Implemented | David |  | Discuss in physical meeting, especially capacity building
SWG Physical meeting | Implemented | David
Info from other standards meeting | Implemented | David |  | Alice to request if SWG can be reviewers of GSIM/GSBPM revision
Microdata in SDMX | Implemented | Zlatina |  | Moved to SDMX 3.0 discussion, such as multiple measures.
GREEN PAPER: IMPROVING SDMX THROUGH AN EVOLUTION OF THE SDMX STANDARDs | Closed | David |  | Secretariat has prioritised the items. Presented to sponsors. Next steps are to map them to work items and action plan in joint WG meeting.
SDMX Glossary: SDMX representation | Closed | David, Danny | https://community.oecd.org/thread/20421 | Create Concept Scheme. PDF. Do this when we revise the glossary.
Review of Guidelines for Confidentiality and Embargo in SDMX | Implemented |  | https://community.oecd.org/message/28573#28573 | Submitted to sec. Add sentence describing difference between C and N from Clearspace thread: N is restricted for an unknown reason and C is confidential for a known reason (identifiable respondents).
Unit of measure, including derived units | Closed |  |  | In parallel with SDMX 3.0 multiple measures
CL_OBS_STATUS reference to "multiple flagging" implementation document | Implemented |  |  | Include in CL_OBS_STATUS revision
Negative multipliers in CL_UNIT_MULT | Implemented | Zlatina, Daniel | https://community.oecd.org/thread/20893 | Now published
Proposal to merge _T and _Z generic codes | Closed | Daniel | https://community.oecd.org/thread/21086 | Need to close discussion, latest proposal is more clarity in the guidelines to help designers and implenentors. Labour WG shows we can't merge _T and _Z in the guidelines
SDMX Maturity Model | Closed | David |  | In the SDMX roadmap. On hold until Modernstats maturity categories are finalised.
Guidelines for a Unit cross-domain concept | Closed | Gabriella, Alice | https://community.oecd.org/message/27311#27311 | Add more detail to SDMX Glossary Unit of Measure term; Ask CSPA Variables group for guidance. Should become part of modelling guidelines. Look to Labour WG discussion for input.
Technical Note revision | Implemented |  |  | Needs a joint TWG/SWG session
Revise the SDMX Glossary | Implemented | David, Danny | https://community.oecd.org/thread/20786 | Published
Multiple measures (in Green paper) | Implemented |  |  | This will start after the Code List extension work item. How does the ECB microdata proposal handle this - review that and link to this paper
Guidelines on representing Methodology change in DSDs | Implemented | Zlatina, Michaela, Daniel | https://community.oecd.org/thread/21087 | David to make editing review, then check if we can publish it.
CL_SEX new version with none breakdown codes | Implemented |  |  | Now published
Revise the Mapping between reference metadata reference frameworks, especially for Global MSD | Closed | Danny |  | After the SDMX Glossary revision.
Review the Code list creation guidelines | Implemented |  |  | Submitted to sec.
Global Conference posters, cheatsheets, papers | Implemented | All | https://community.oecd.org/thread/22256 | Publish the cheat sheets on SDMX.org
Create Code Lists for the guideline for time transformation, e.g.CL_TIMETRANS_TYPE. Code List ID: CL_TIMETRANS_PER. Example for composite CL_TIMETRANS: working off the guideline for time transformation | Closed | Laura, David |  | David to upload to production GR
Data provisioning definition guidelines | Parked | Laura, David | https://community.oecd.org/message/49157#49157 | David making an edit of the guideline. Need more info on registrations. David waiting from MT about it
Pilot review of Prices DSD | Implemented | Michaela, Ian
Revise the DSD guidelines | Parked |  |  | Especially sections that are in conflict with modelling guidelines
OBS_STATUS revision, including "Revised" code | Closed |  |  | ECB to follow up internally
Versioning and isFinal Guidelines revision | Parked | David | https://community.oecd.org/thread/23473 | Part of SDMX 3.0, need to involve TWG
Business case for SDMX | Implemented | Danny | https://github.com/SDMX-SWG/Business-Case | Published - Stephane will ask management for a French translation
Use of SDMX annotations | Implemented |  |  | Part of SDMX 3.0. Jens Dosse is the leader
Guidelines on the use of SDMX for countries with little IT infrastructrure (SDMX-light) | Closed |  |  | New (11/7/2018): Action mentioned in the Roadmap 2020
Guidelines for the usecase of SDMX formats (e.g.CSV). When to use which format. | Cancelled |  |  | Is this actually in the roadmap? Check it.
Update of "Possible ways of implementing the observation status concept" | Implemented | David | https://community.oecd.org/thread/23956 | Awaiting SDMX sec. response. Follow up with BIS on GESMES issue as per Daniel's email 26/2
OBS_STATUS clarification between Estimated and Imputed | Implemented | Danny | https://community.oecd.org/thread/23471 | Pubished in March 2019
Creation of a page for the Global Registry | Implemented | Danny Delcambre, David | https://community.oecd.org/thread/21458 | Redesign of the current landing page, making it more useful. Creation of a page for the Global Registry (reusing info from former page https://registry.sdmx.org/). This page could be a simple introductory page, providing general info on the GR and referring to the actual place where the Registry is held. Other questions are e.g.: What do we do with the existing documentation ? It can partially prove useful but looks a bit outdated (especially for screenshots) and would therefore need to be updated. The new GR page should have the same feel and look of the sdmx.org. David to follow-up ECB and Secretariat. . This is on the test instance of the GR.
Addition of generic codes in all new and revisions of existing CDCLs | Ongoing | SWG | https://community.oecd.org/thread/14159 | Add the generic code as we create new CDCLs or new versions.
Extension of CL_OBS_STATUS with two new codes for Education DSD purposes | Implemented | Javier | https://community.oecd.org/thread/14150?start=150&tstart=1 | Accepted
Clean up the ClearSpace page | Closed | David |  | Many discussions could be archived (an "Archives" sub-section already exists). Asked Clearspace team but no quick bulk archiving solution
Checklist for SDMX Design Projects | Implemented |  | http://www1.unece.org/stat/platform/display/SDMXPM/Checklist+for+SDMX+Design+Projects+Home | Published. David to present it at the end of the year to standards team as an example of usng GDBPM logic for better readability
Guidelines for SDMX Concept Roles. | Implemented | Laura, David | https://community.oecd.org/thread/18002 | Published
CDCL for "Time Transformation' | Implemented |  |  | Accepted
SDMX Message Header Guidelines | Implemented | Zlatina | https://community.oecd.org/thread/19404 | To consolidate the document we have now in order to discuss the proposal
CL_AREA | Implemented | Ian | https://community.oecd.org/thread/13975 | Incorporate M49 and ISO hierarchy in separate branches. Top level nodes: M49, ISO3166_2. Add sentence to guideline about the StructureSet.
Terms of Reference for the SWG | Implemented | David | https://community.oecd.org/thread/14273 | To review by SWG
Modelling Statistical Domains in SDMX | Implemented | David, Daniel, Ian, Laura, Zlatina | https://community.oecd.org/docs/DOC-115617 | In public review, need to address the feedback, refresh the document
Creation of a page for the Global Registry | Implemented | Danny Delcambre, David | https://community.oecd.org/thread/21458 | Redesign of the current landing page, making it more useful. Creation of a page for the Global Registry (reusing info from former page https://registry.sdmx.org/). This page could be a simple introductory page, providing general info on the GR and referring to the actual place where the Registry is held. Other questions are e.g.: What do we do with the existing documentation ? It can partially prove useful but looks a bit outdated (especially for screenshots) and would therefore need to be updated. The new GR page should have the same feel and look of the sdmx.org. David to follow-up ECB and Secretariat. . This is on the test instance of the GR.
Review and update SDMX checklist for the design of SDMX projects | Implemented | Danny, David | https://statswiki.unece.org/display/SDMXPM/Checklist+for+SDMX+Design+Projects+Home | Some broken links, outdated screenshots. Also include new guidelines or new versions. Danny reviewed introduction and first pillar ("Specify needs"). David to review next pillar. Put warning about DESIGN pillar nto in synch with modelling guidelines
CL_FREQ: allowing new frequencies to be defined | Implemented | Yamil | https://community.oecd.org/thread/23909 | Approved.
CL_CONF_STATUS discussion: clarificaiton on A, O, T, G and M text | Closed |  | https://community.oecd.org/thread/16403
CL_TRANSPORT_MODE proposal | Parked | Helen, David | https://community.oecd.org/thread/23992 | David waiting for feedback from ITF colleague on the UN proposal. David to follow up with ITF
Review SEEA Global DSD | Closed |  |  | Daniel to request a reviewer from the SWG
CL_UNIT_MEASURE and unit guidelines | Implemented | Stephane, Anastassia, Zlatina,Gyorgy | https://github.com/SDMX-SWG/Public-review-Unit-of-Measure-guidelines | Approved for publication 12/12/2025
Review of SDG Global DSD | Closed | Michaela, Laura
CDCL list for Education Status | Closed | David |  | Luca's response: One code list from the Education project that could definitely be proposed as a cross-domain code list is the code list for Education Level. You will now find it in the Global registry. The only other possible candidate would be the code list for Fields of Education, but I think there is much less interest on the latter.
Implemented
Controlled Vocabulary for Annotations |  |  |  | (added by Danny 13/12/2019)
Annotations guideline | Implemented | David |  | Approved and published
CL_DEG_URB: Code list for degree of urbanisation | Implemented |  |  | Approved by the secretariat, need to publish it.
SDMX Registries and duplicate artefact identifiers | Closed | Zlatina | https://community.oecd.org/message/48956#48956 | Create a guideline recommendation to at least: - avoid having the same identifier for different artefacts in different registries - recommend where to store different types of artefacts (global, shared, local) - provide guidance on how to document artefacts for user-friendly documentation in registries Proposal solution (all 3 required): - the local MA artefacts in the GR being moved to the local registry and referenced from there, not duplicated in the GR. Any collisions will presumably be detected on upload to the local registry - changing the MA of the GR artefact to the project’s ownership group - MA ID needs to be globally unique and assigned to a specific registry Previous drafts on this issue: - (2015) Recommendations on Avoiding Duplication of Content in Multiple SDMX Registries https://community.oecd.org/message/32716#32716 - (2018) ISSUE NOTE ON SDMX REGISTRIES https://community.oecd.org/thread/19882 Zlatina will post the ECB information on how they deal with this
CL_BREAK | Implemented | Yamil | https://community.oecd.org/message/48981 | Yamil to publish it
Update CL_CURRENCY | Cancelled |  |  | Add New Belarus Rouble (BYN, valid since 2016)
CL_VALUATION | Parked | David |  | From National Accounts. Check with latest NA proposal before making it a CDCL
Next version of the SDMX Glossary | Implemented | Danny, David | https://community.oecd.org/thread/27159 | Send back to SDMX Secretariat, ask to publish
Other codelists from Global DSDs | Closed |  | https://github.com/SDMX-SWG/CDCL | AGGREGATION_OPERATION Aggregation Operation Representation of the calculation type when a single value is calculated from a collection of values. HOURS_TYPE Type of hours Type of hours worked VALUE_TYPE Type of value Type of value SOURCE_TYPE Data Source LABOUR_FORCE_STATUS Labour force status WORKER_STATUS Status of Worker EDUCATION_LEV Education level (eg, ISCED) OCCUPATION Occupation (eg, ISCO) MIGRANT_STATUS Migrant status PROD_UNIT Type of Production Unit, e.g. Informal, Formal, Household
CL_SEX revision | Parked | Maarja |  | European commission codelist feedback still pending
Adding NAICS to CL_ACTIVITY | Implemented | Stephane, David |  | Sent to secretariat. Passed without comment, can publish it
Review the Global Metadata Concept Scheme | Parked | David |  | Parked until Q1 2022. Add DATA_LAST_UPDATE. Consider changes from SDMX Glossary 2.1, ESQRS, SDGs, other frameworks
Flagging of the use of perturbative Statistical Disclosure Control methods | Parked | Christine, Marjajamsa | https://community.oecd.org/thread/27997 | Parked until Eurostat internal analysis is complete
Confidentiality Status revision | Implemented | Yamil | https://community.oecd.org/thread/28697 | Published
Observation Status: new reliability codes | Closed | Dany | https://community.oecd.org/thread/28721 | Consensus to put these new codes in new reliability codelist. Summarise SWG idea of separate codelist on the Clearspace thread. Dany to create document for CL_RELIABILITY
Organise SWG 2021 virtual meeting | Closed | David |  | Create Doodle poll
Review CL_ORGANISATION - new version | Implemented | David |  | Sent to secretariat. Passed without comment, can publish it
Revision of the Modelling guidelines | Parked | David | https://sdmx.org/wp-content/uploads/Modelling-statistical-domains-in-SDMX-v2-201806.docx | Reformat from the physical meeting
Guidelines for Structural Metadata Governance | Implemented | David | https://community.oecd.org/thread/29612 | Published
Link between SDMX and GSBPM sub-activities | Closed | David |  | Initiative started in the ModernStats community. David to make a mapping between SDMX and GSBPM sub-process
CL_RELIABILITY | Implemented | Yamil | CL_RELIABILITY | Yamil to publish it
Concept Roles: Add COUNT role | Implemented | David, Yamil | https://community.oecd.org/thread/18002 | Yamil to publish
CL_GENDER codelist | Parked |  |  | European commission codelist feedback still pending. IMF and OECD expressed interest
Add license to cross-domain artefacts and guidelines | Implemented | Yamil | https://community.oecd.org/thread/30009 | Yamil to add this
Scope of use of SDMX Global Registry | Closed | David |  | Several comments from SWG members. Feed them into the discussion.
COICOP 2018 | Implemented | Galya |  | Published
Global Registry translation collaborative process | Closed | Stephane | https://community.oecd.org/thread/31364 | Link this to "Translations of cross-domain artefacts: Process and governance"? Stephane to update draft guideline, put on community site for discussion
CL_FREQ: put 2.1 in GR | Implemented | David |  | Add this to the global registry
Organise SWG annual meeting | Closed | David |  | SDMX Expert group meeting. Modelling guidelines, propose Unit of measure v1.0?, Name of CL_AGGREGATION_OPERATION?, Linking CL_ORGANISATION to Agency Scheme, Future work brainstorm
CL_AREA: Change Turkey name | Implemented | David |  | Released new patch version with Turkey change
CL_STATISTICAL_OPERATION | Implemented | Angela,Laura | https://community.oecd.org/thread/31384 | Published
Vintages guidelines | Implemented | Yamil, Zlatina, Bernadette, (consultant:Abdulla) |  | David has sent it to secretariat 27/6/2025. BIS want to have a reference to how to use the API for vintages. The TWG will author those tech. guidelines so we wait for them to put the link into SWG guidelines
Strategical document (not a process) on structural metadata harmonisation | Parked | David, Fadhila |  | Fadhila will make a problem statement. Parked as the scope is unknown.
Revision of the Guidelines for the Creation and Management of SDMX Code Lists | Implemented | Stephane, Luca, Abdulla |  | Published
Ontologies for SDMX | Open | Laura, Dany, FAO colleagues | https://github.com/sdmx-twg/twg/tree/develop/workpackages/sdmx_lod | Laura to post content in SWG community. Use cases/implementation guide to be provided. Mapping being done between SDMX, skos, xkos, dcat, datacube. Need to decide the next artefacts to include in the ontology.
Logical data modelling | Parked | Daniel |  | Bernadette will ask Daniel. Dependent on annotations/object model proposal. After that it will be shared.
Guideline for Hierarchical codelists | Implemented | Yamil, Dani, Luca,Laura,Fadhila,Galya |  | David has asked Glenn to confirm it's approved 14/8/2025
Annotations guideline revision | Parked | David, Daniel |  | Park until at least the joint WG meeting in May
Translations of cross-domain artefacts: Process and governance | Parked | David, Dani, Stephane, Abdulla, Eduardo |  | BIS was leading this, is it now Eurostat?
Versioning for SDMX 3.0 | Implemented | Allen Boddie (TWG) |  | Published
Microdata for SDMX 3.0 | Open | David,Angela,Laura,Bilyana,Olivier, Galya |  | Final draft being prepared by Olivier
Link the SDMX-TWG github examples to SDMX 3.0 guidelines. Have examples for guidelines in the TWG github | Ongoing | All
Annotation guideline updates | Parked | David |  | Yes it is, update after the OECD migration
Using SDMX to maintain classifications | Parked | David |  | UNSD developing a template for maintaining classifications in SDMX. Pilot is M49 maintenance. Will implement in 2026.
SDMX adoption for the enterprise | Open | David |  | Maturity model agreed, to send for review. Cookbook drafting started.
Update Annotations guideline | Implemented | David |  | Issues raised by Alan at IMF. Something else from OECD? Possibility of including regex for annotation values.
Arrange 2025 SDMX SWG annual meeting | Implemented | David |  | Meeting side event at SDMX GC. Tuesday at lunch 12-30 to 14:00. Room is not for a hybrid meeting, we could do something with Teams. David to send meeting event
CL_CONF_STATUS X to P, new version | Implemented | David |  | Problem with code X in Global registry. it should be P as in Guideline with same label. SWG decided to label X as deprecated and make a minor change to 1.4.
NACE 2.1 codelist authoring | Implemented | Galya |  | Approved for publication 12/12/2025
CL_OBS_STATUS revision | Implemented | David |  | Approved for publication 12/12/2025
License for SDMX guidelines | Parked | David |  | The current license is CC BY-SA 4.0. Is it too restrictive for companies wanting to develop monetized apps?
CL_ORGANISATION: Invalid syntax in section 1 and 2, missing paranthese | Closed | David |  | Syntaxes are missing a paranthese. The paranthesis was added to say AA(A)(_AA(A))(0)*
CL_ORGANISATION: Coding convention is unclear, especially for national private companies. | Implemented | David |  | Secretariat approved. David to ask for publication.
CL_ORGANISATION: Using it for agency schemes | Closed |  |  | Clarify if and how it should be used for agencies. Wrote a section on using it for Agencies. Sent the email to SGDS group on this as it has to be correct for SGDS. Include more examples and upload the doc to community site
Update SDMX Glossary | Open |  |  | Incorporate SDMX 3.0 terms. Unit of Measure, Microdata, Linked Open Data. Decide whether to wait for dependency TFs to conclude, e.g. on Microdata. Request to share additional concepts before addition (this list doesn't exist yet).
Update existing guidelines | Ongoing |  | https://one-communities.oecd.org/community/sdmx_swg/SitePages/SDMX-Guidelines-Review.aspx | See linked document
Move guidelines to new format/platform | Open |  |  | This is a pilot project by HMS company. Could semantic versioning be part of this, to reference tech guidelines. Yamil has tested the BIS AI bot if it can parse the current PDF/Word guidelines - it cannot. This gives more credence to this project
CL_CIVIL_STATUS revision and CL_GENERIC_CODE | Open | David |  | David to finalise proposal for joint meeting. UNSD remarks that the generic codes are missing: _Z, _U, _O, _T
Geospatial codes and guidelines | Open | Yamil |  | From Marco Marini: The SWG could create a standard geospatial codelist linked to the “area” codelist. There are also grid coordinates like Uber H3 which can be transformed into SDMX geospatial codelists. Yamil will discuss with Matt on whether this is a gap with SDMX 3.0 to represent geospatial, or if there is no gap but we need a guideline
Semantics in SDMX | Parked | David |  | Parked until discussions move forward.
Minimum Viable Metadata (MVM) for visibility and discovery | Parked | David |  | Create a page on community site with starting suggestions and details
Unit of measure codelists | Open | David,Gyorgy |  | First priority is the MES global DSD revision, therefore this codelist is starting that scope.
Review of CL_ACTIVITY 2.0.0 for MES group | Implemented | Ioulia,Galya |  | Galya to update codelist sheet with properties and whether it's annotation or description
Sentinel values | Open | Eduardo, Galya, David |  | Supporting standards are gathering members of this WG. Ensure the gaps from microdata WG are included
Extending codelists horizontally, e.g. with new languages | Open | David |  | Joint working group. Candidate is using new artefact(s).
Update of SDMX cross-domain category scheme |  |  |  | Abdulla says: it’s been a while since CSA v2.0 was published at https://unece.org/statistics/documents/2022/05/working-documents/classification-statistical-activities-csa-20-and, it’s more relevant than v1.0 and is available in English, French, and Russian. It should be pretty straightforward to update the category scheme, and it would be very useful particularly for users of the .Stat Suite and other dissemination platforms.

## Lookup
Category | Status
Documentation | Open
Matrix | Cancelled
Artefact | To be changed
Task | Implemented
Closed
Parked
Ongoing